## Group member 4
To-do list Project 3
To be completed by: |  | FAHIM(PROJ MANAGER)12/14/2025 |  | Names: Esfar, Justin, Sayantan, Fahim, Yousuf
Deadline: |  | 2025-12-14 |  | Date: 12/16/2025
Project 3 Group Database Design
% done | Phase | Start By | Original Due By2 | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2025-12-01 | 2025-12-01 | 2025-12-01 |  | Group meets to review instructions, confirm deliverables, and assign roles.
90% | Schema & UDT Design | 2025-12-02 | 2025-12-03 | 2025-12-04 |  | Created logical database schemas ([Data], [Udt], [Process], [DbSecurity]). Created UDTs such as SurrogateKeyInt and CodeVarchar10.
90% | Dimension Table Design | 2025-12-04 | 2025-12-05 | 2025-12-05 |  | Normalized attributes into dimension tables (Department, Instructor, Course, BuildingLocation, RoomLocation). Implemented unique constraints.
95% | Fact Table & Relationships | 2025-12-06 | 2025-12-07 | 2025-12-07 |  | Implemented Section fact table to store surrogate keys from all dimension tables. Added foreign key constraints with ON DELETE CASCADE.
85% | ETL / Data Transformation | 2025-12-08 | 2025-12-09 | 2025-12-09 |  | Created ETL stored procedures to load each dimension table independently. Applied advanced string parsing logic (PATINDEX, SUBSTRING).
95% | Auditing & Workflow Tracking | 2025-12-09 | 2025-12-10 | 2025-12-11 |  | Integrated Process.TrackWorkFlow auditing procedure into all ETL processes
90% | Testing & Validation | 2025-12-11 | 2025-12-12 | 2025-12-12 |  | Validated referential integrity, row counts, and surrogate key mappings across all dimension and fact tables
95% | Final Script Compilation | 2025-12-12 | 2025-12-13 | 2025-12-13 |  | Prepared presentation script and technical walkthrough demonstrating Star Schema design, and ETL logic
95% | Group Presentation & Recording | 2025-12-13 | 2025-12-14 | 2025-12-16 |  | Delivered and recorded a structured group presentation explaining the Star Schema design, ETL workflow, auditing mechanisms